## Summary
Enigmatrix — Module 1 Development Evaluation
Whole-project build vs the 16_M1_Development_Roadmap · owner Mohamed M.R.I (215075J) · generated 2026-06-30 (through Session 65)
Metric | Value | Notes
Total features tracked | 212 | FEATURES.md register (F-01 … F-228)
Features Done | 204 | 🟢 shipped
Features In Progress | 4 | 🟡 scaffolded / partial
Features Not Started | 3 | 🔲 planned
Feature completion % | 96.23% | Done ÷ total
Roadmap completion (weighted) | 57.5% | Done=1, In Progress=0.5
Phase 1 — Foundation | 100% | ✅ complete
Phase 2 — Ingest + Extract | 100% | ✅ complete (+ upgrade)
Phase 3 — Annotation + Classify | 50% | 🟡 code-complete; needs labels+training
Phase 4 — Schedulers + Alerts + Lag | 0% | 🔲 not started
Phase 5 — Findings + Survey | 16.67% | 🟡 survey partial; findings pending
Verdict
Phases 1–2 shipped in production (ingest→extract→preprocess + a research-grade measurement/dataset layer). Phase 3 is now CODE-COMPLETE end-to-end (annotation prep, model, eval, ONNX inference wiring) — the classifier turns extracted gazettes into their concept. The only remaining gates are human annotation to ≥800 gold labels (3c) and the GPU training run (3d), after which eval (3e) + deploy (3f) run. Phases 4–5 (alerts, lag dataset, F1–F6 findings, survey-at-scale) are the research-output frontier.

## Feature Register
ID | Session | Area | Status | Feature
F-01 | — | Platform/Foundation | Done | Monorepo scaffold (`backend/ frontend/ ml/ infra/ docs/tracker/ scripts/`) + root configs ¦ 🟢 ¦ `BUILD_02 §1–§6` ¦ `tree -L 2` matches §1 la
F-02 | — | Platform/Foundation | Done | Dev infrastructure: `docker-compose.dev.yml` + `infra/postgres/init.sql` ¦ 🟢 ¦ `BUILD_04 §2` ¦ `make up` brings Postgres healthy ¦
F-03 | — | Platform/Foundation | Done | `.gitignore`, `.env.example`, `Makefile`, root `README.md`, pre-commit ¦ 🟢 ¦ `BUILD_01 §6` ¦ `pre-commit install` succeeds ¦
F-04 | — | Platform/Foundation | Done | Tracker bootstrap (`docs/tracker/{README,FEATURES,SESSIONS,CHANGES}.md`) ¦ 🟢 ¦ this plan ¦ All four files exist ¦
F-05 | — | Platform/Foundation | Done | FastAPI app: `main.py`, `settings.py`, `logging_config.py`, `exceptions.py`, `deps.py` ¦ 🟢 ¦ `BUILD_03 §3–§7` ¦ `GET /health` returns 200 (v
F-06 | — | Platform/Foundation | Done | Pydantic v2 settings with `DATABASE_URL` (asyncpg) + `JWT_SECRET` + `CORS_ORIGINS` ¦ 🟢 ¦ `BUILD_03 §3` ¦ `app/settings.py` boots with `.env`
F-07 | — | Platform/Foundation | Done | SQLAlchemy 2.0 async session + `DeclarativeBase` + `TimestampMixin` ¦ 🟢 ¦ `BUILD_04 §3` ¦ `db_session` fixture in `conftest.py` validates ro
F-08 | — | M1 Awareness | Done | ORM models: `User`, `SMEProfile`, `SurveyResponse`, `AuditLog` ¦ 🟢 ¦ `BUILD_04 §5` + `research/06 §4` ¦ `python -m compileall app` clean; mo
F-09 | — | Platform/Foundation | Done | Alembic init + initial migration (`202605080001_initial_schema.py`) ¦ 🟢 ¦ `BUILD_04 §4` ¦ `alembic upgrade head` succeeds on fresh DB (verif
F-10 | — | Platform/Foundation | Done | Auth: `core/security.py` (bcrypt + HS256 JWT access/refresh) ¦ 🟢 ¦ `BUILD_06 §2` ¦ `tests/unit/test_security.py` round-trips access + refres
F-11 | — | Platform/Foundation | Done | Auth service + schemas + router (`/auth/register`, `/auth/login`, `/auth/refresh`) ¦ 🟢 ¦ `BUILD_06 §3–§5` ¦ Integration test passes register
F-12 | — | M1 Awareness | Done | RBAC: `get_current_user`, `require_admin`, `require_annotator` deps ¦ 🟢 ¦ `BUILD_03 §6` + `BUILD_06 §6` ¦ Integration test asserts SME → 403
F-13 | — | Platform/Foundation | Done | Inbound rate limit on `/auth/login` and `/auth/register` (slowapi) ¦ 🟢 ¦ `BUILD_06 §9` ¦ `core/rate_limit.py` wired in `main.py`; auth route
F-14 | — | M1 Awareness | Done | `users.py` router: `GET /api/v1/users/me`, admin-only `GET /api/v1/users` ¦ 🟢 ¦ `BUILD_03 §13` ¦ `api/v1/users.py` returns user + profile ¦
F-15 | — | M0/Survey | Done | `surveys.py` router: `POST /surveys/{instrument}/submit`, `GET /surveys/{instrument}/responses` (admin) ¦ 🟢 ¦ this plan ¦ Integration test e
F-16 | — | Platform/Foundation | Done | Audit-log writes on auth events ¦ 🟢 ¦ `BUILD_06 §10` ¦ `auth_service` writes `auth.register`, `auth.login.success/failure`, `auth.refresh` r
F-17 | — | M3 Risk | Done | Module-router 501 stubs (`regulations`, `qa`, `risk`, `verify`) ¦ 🟢 ¦ this plan ¦ Integration test asserts each returns 501 + `code: not_imp
F-18 | — | M1 Awareness | Done | `seed_dev.py`: admin + annotator + sample SME ¦ 🟢 ¦ `BUILD_04 §8` ¦ `make seed` is idempotent ¦
F-19 | — | Platform/Foundation | Done | Next.js 14 app (App Router, TS, Tailwind) ¦ 🟢 ¦ `BUILD_05 §1` ¦ `package.json` + `next.config.mjs` + `app/layout.tsx` present ¦
F-20 | — | Platform/Foundation | Done | shadcn-pattern primitives: button, input, label, card, badge, alert, skeleton, dropdown-menu, select, radio-group, checkbox, table, toaster,
F-21 | — | Platform/Foundation | Done | Domain-tuned theme tokens (trust-blue 217 91% 50% + amber 38 92% 50%) for light + dark ¦ 🟢 ¦ this plan + `BUILD_05 §2` ¦ `app/globals.css` d
F-22 | — | Platform/Foundation | Done | `next-themes` light/dark/system toggle in topbar ¦ 🟢 ¦ this plan ¦ `components/layout/theme-toggle.tsx` mounted in `Topbar` ¦
F-23 | — | Platform/Foundation | Done | Multilingual fonts via `next/font` (Inter + Noto Sans Sinhala + Noto Sans Tamil) ¦ 🟢 ¦ `BUILD_05 §3` ¦ `app/layout.tsx` registers all three
F-24 | — | Platform/Foundation | Done | `next-intl` with `en/si/ta`; locale switcher in topbar ¦ 🟢 ¦ `BUILD_05 §4` ¦ `i18n.ts` + 3 messages files; `LocaleSwitcher` writes `NEXT_LOC
F-25 | — | M0/Survey | Done | API client (`lib/api/client.ts`) with `ApiError` + bearer token plumb ¦ 🟢 ¦ `BUILD_05 §5` ¦ `lib/api/{client,auth,surveys,users}.ts` ¦
F-26 | — | Platform/Foundation | Done | `lib/auth/{session,roles}.ts` — server-side `requireUser()` / `requireRole()` ¦ 🟢 ¦ `BUILD_06 §8` ¦ `(app)` and `(admin)` layouts call them
F-27 | — | Platform/Foundation | Done | TanStack Query + theme provider in `components/providers.tsx` ¦ 🟢 ¦ `BUILD_05 §9` ¦ Query client mounted under `ThemeProvider` ¦
F-28 | — | Platform/Foundation | Done | `/login` page (zod + react-hook-form + shadcn) ¦ 🟢 ¦ `BUILD_06 §8` ¦ Posts to backend, calls `/api/auth/establish`, redirects to `next` ¦
F-29 | — | M1 Awareness | Done | `/register` page (email + password + SME profile fields) ¦ 🟢 ¦ `BUILD_06 §3` ¦ Creates user + profile, then auto-logs-in ¦
F-30 | — | Platform/Foundation | Done | Cookie route handlers: `/api/auth/establish`, `/api/auth/token`, `/api/auth/logout` ¦ 🟢 ¦ `BUILD_06 §8` ¦ HTTP-only cookies set on login, cl
F-31 | — | Platform/Foundation | Done | Auth-guarded `(app)` layout + admin-guarded `(admin)` layout + middleware fast-path ¦ 🟢 ¦ `BUILD_05 §7` ¦ `middleware.ts` redirects unauth'd
F-32 | — | Platform/Foundation | Done | Topbar with role badge + email + theme + locale + logout ¦ 🟢 ¦ this plan ¦ `components/layout/topbar.tsx` ¦
F-33 | — | M0/Survey | Done | Awareness question bank `lib/surveys/awareness.ts` (12 items) ¦ 🟢 ¦ `research/08` + plan ¦ All 6 question kinds covered (single, multi, like
F-34 | — | M0/Survey | Done | Reusable `SurveyForm` + `QuestionRenderer` for all 6 kinds ¦ 🟢 ¦ `BUILD_05 §11` ¦ Each kind validates + serialises to backend `SurveyAnswerI
F-35 | — | M0/Survey | Done | `/surveys/awareness` page submits to `POST /surveys/awareness/submit` ¦ 🟢 ¦ this plan ¦ On success, router pushes to `/surveys/awareness/tha
F-36 | — | M0/Survey | Done | `/surveys/awareness/thank-you` confirmation ¦ 🟢 ¦ this plan ¦ Renders w/ "Back to dashboard" CTA ¦
F-37 | — | M0/Survey | Done | Admin response list `/admin/surveys/awareness` (table + total + pagination params) ¦ 🟢 ¦ this plan ¦ shadcn `Table` lists submissions groupe
F-38 | — | M0/Survey | Done | Admin user list `/admin/users` (read-only, role badges) ¦ 🟢 ¦ this plan ¦ shadcn `Table` shows email + role badge + sector + region ¦
F-39 | — | M3 Risk | Done | "Coming soon" stubs for `/regulations`, `/qa`, `/verify`, `/risk` ¦ 🟢 ¦ `BUILD_05 §10` ¦ Each renders `<ComingSoon>` with the relevant `BUIL
F-40 | — | M0/Survey | Done | Backend integration test `test_survey_flow.py` (httpx + Postgres testcontainer) ¦ 🟢 ¦ plan + `BUILD_15 §6` ¦ Two test cases: full register/l
F-41 | — | Platform/Foundation | Done | Backend unit tests for `core/security` (bcrypt + JWT round-trip) ¦ 🟢 ¦ this plan ¦ `tests/unit/test_security.py` ¦
F-42 | — | M0/Survey | Done | Playwright E2E `auth_survey_admin.spec.ts` ¦ 🟢 (script ready) ¦ plan ¦ Runs on `make dev-frontend` + seeded backend; needs runtime verificat
F-43 | S3 | Platform/Foundation | Done | Now 12 files
F-44 | — | M2 Knowledge | Done | Backend schema: `regulatory_domains`, `sectors`, `m2_questions`, `m2_knowledge_scores`, `m3_compliance_history`, `m3_behavioural_signals` +
F-45 | — | M2 Knowledge | Done | M2 question bank seed (`seed_m23_questions.py`) — 9 domains + 12 sectors + 40 canonical questions verbatim from `module_2_and_3` PART A ¦ 🟢
F-46 | — | M2 Knowledge | Done | Cross-module-linkage rules (`m2_linkage_rules.py`) — awareness → M2 question selection ¦ 🟢 ¦ this plan ¦ Rule fires on `awareness.v1.q04 = n
F-47 | — | M2 Knowledge | Done | M2 scoring engine (`m2_scoring.py`) — mcq, scenario, numeric, ordered_steps with partial-credit, open with element-matching ¦ 🟢 ¦ this plan
F-48 | — | M2 Knowledge | Done | M2 service: `questions_for_sme`, scoring on submit, `recompute_knowledge_score` cache write ¦ 🟢 ¦ this plan ¦ `test_m2_flow.py` asserts `is_
F-49 | — | M2 Knowledge | Done | M3 service: history submit, behavioural submit, combined `risk-signals` view (BUILD_00 contract) ¦ 🟢 ¦ this plan ¦ `test_m3_flow.py` asserts
F-50 | — | M2 Knowledge | Done | M2 + M3 routers (`/api/v1/m2/*`, `/api/v1/m3/*`); `SupportedInstrument` extended to `["awareness","knowledge","vulnerability"]` ¦ 🟢 ¦ this p
F-51 | — | M2 Knowledge | Done | Frontend conditional questions: shared `types.ts`, `dependsOn` evaluator, renderer `useWatch`, submit-time stripping ¦ 🟢 ¦ this plan ¦ M3 vu
F-52 | — | M2 Knowledge | Done | Frontend SME pages: Surveys hub `/regulations`, Knowledge survey + thank-you, Vulnerability survey + thank-you, Risk read-only `/risk` ¦ 🟢 ¦
F-53 | — | M2 Knowledge | Done | Frontend admin pages: M2 question bank with inline Verify, M2 scores, M3 risk-signals ¦ 🟢 ¦ this plan ¦ Admin `/admin/m2/questions` Verify a
F-54 | — | M2 Knowledge | Done | UX polish: sticky `SurveyProgress` (visible-only denominator), `useAutosave` to localStorage every 10s with Resume banner, `SurveyErrorSumma
F-55 | — | M2 Knowledge | Done | i18n parity: en/si/ta all carry the new `surveys.hub`, `surveys.knowledgeTitle`, `risk`, `admin` keys (116 keys each) ¦ 🟢 ¦ this plan ¦ JSON
F-56 | — | M2 Knowledge | Done | Backend integration tests (`test_m2_flow.py`, `test_m3_flow.py`) + unit (`test_m2_scoring.py`) + Playwright (`surveys_knowledge_vulnerabilit
F-57 | S5 | Platform/Foundation | Done | bcrypt pin `>=4.0,<4.1` in `backend/pyproject.toml` — stops the recurring passlib `__about__` AttributeError + 72-byte ValueError on hash. ¦
F-58 | S5 | Platform/Foundation | Done | Defensive 72-byte UTF-8 truncation in `app/core/security.py` — both `hash_password` and `verify_password` now route every secret through `_t
F-59 | S5 | Platform/Foundation | Done | `.env.example` `CORS_ORIGINS` ships in JSON-array form (`["http://localhost:3000"]`) with an inline comment. ¦ 🟢 ¦ session 5 (Pydantic Setti
F-60 | S5 | Platform/Foundation | Done | `docs/SETUP/09_Troubleshooting.md` updated: entry 9 rewritten with the actual root cause + actual fix; new 9b (long unicode passwords), 25b
F-61 | S5 | Platform/Foundation | Done | CORS preflight 400 fix in `app/main.py` — strip trailing slash from every entry before passing to `CORSMiddleware`. Pydantic v2's `AnyHttpUr
F-62 | S5 | Platform/Foundation | Done | Auth diagnostics + DB-inspection toolkit. New `make doctor` (`backend/app/scripts/doctor.py`) checks bcrypt version, hash round-trip, and th
F-63 | S5 | M0/Survey | Done | App-Router parallel-pages collision fix. The admin awareness response list was at `/admin/surveys/awareness`, but Next.js strips route group
F-64 | S5 | Platform/Foundation | Done | `useAutosave` no longer reaches into `useFormContext()` — the call ran before `<FormProvider>` mounted, returning `null` and crashing every
F-65 | S6 | M0/Survey | Done | Unified `survey_questions` schema (rename of `m2_questions` + `module_number`/`linked_regulation_id`/`next_question_rules`/`is_required`/`in
F-66 | S6 | M3 Risk | Done | Idempotent seed scripts: `seed_regulations` (5 canonical regs), `seed_awareness_questions` (12 M0 with cross-module rules), `seed_vulnerabil
F-67 | S6 | M0/Survey | Done | Flow engine (`survey_question_service`): `start_flow`, `next_question`, `_resolve_rule` (predicates `answer_eq` / `answer_in` / `answer_lt`
F-68 | S6 | M0/Survey | Done | M1 regulation service: `list_regulations`, `get_regulation`, `get_regulation_sectors`, `create_regulation`, `update_regulation`, `verify_reg
F-69 | S6 | M0/Survey | Done | Backend routers + schemas: `/api/v1/survey-flow/{start,answer}` (SME) and `/api/v1/m1/regulations/*` (admin CRUD + `/{id}/public` SME-safe r
F-70 | S6 | M3 Risk | Done | M3 projection on `survey_service.submit`: `_project_m3_snapshots` writes `module_number = 3` answers into `m3_compliance_history` / `m3_beha
F-71 | S6 | M0/Survey | Done | Unified `/surveys` page (server) + `SurveyWizard` client + `flow-question-to-ui.ts` adapter (single/multi/likert/date/numeric/short_text/ord
F-72 | S6 | M0/Survey | Done | i18n parity: new `surveys.flowTitle / flowSubtitle / questionOfTotal / crossModuleHint` keys added to `en/si/ta`. ¦ 🟢 ¦ session 6 ¦ All thre
F-73 | S6 | M2 Knowledge | Done | Follow-up migration `202605100002_relax_survey_question_columns.py` — drops `NOT NULL` from `survey_questions.domain_code` and `knowledge_ty
F-74 | S7 | M0/Survey | In Progress | Phase A landed (session 7).
F-75 | S6 | M3 Risk | Not Started | Backend tests: extend `test_m2_scoring.py` (M3 answers don't get scored); new `test_survey_flow.py` (start → answer → branch → null, incl. r
F-76 | S6 | M0/Survey | Not Started | Playwright spec: `surveys_unified_flow.spec.ts` walking the VAT-no branch into `VAT_FACT_002` and verifying the module-accent swap ¦ 🔲 ¦ ses
F-77 | S7 | M0/Survey | Not Started | Phase B (deferred).
F-78 | S7 | M0/Survey | Done | New `Tabs` primitive (`components/ui/tabs.tsx`) on `@radix-ui/react-tabs` (already in deps). Reused by the regulation form's EN/SI/TA panels
F-79 | S7 | M2 Knowledge | Done | Per-module accent extended into admin shells: `module-m2` wraps `/admin/m2/questions` and `/admin/m2/scores`; `module-m3` wraps `/admin/m3/r
F-80 | S7 | M0/Survey | Done | i18n keys for the regulations admin surface (en/si/ta parity at 185 keys each): `nav.adminRegulations`, `regulations.{listTitle, listSubtitl
F-81 | S7 | M1 Awareness | Done | Constants extracted to single source of truth: `lib/constants/domains.ts` (DOMAINS) and `lib/constants/sectors.ts` (SECTORS + DOCUMENT_TYPES
F-82 | S8 | Platform/Foundation | Done | Hotfix: parallel-pages route collision
F-83 | S8 | Platform/Foundation | Done | App-shell redesign.
F-84 | S8 | Platform/Foundation | Done | New shell primitives + glue: `components/ui/avatar.tsx` (initials fallback), `components/ui/breadcrumb.tsx`, `components/ui/tooltip.tsx` (ra
F-85 | S8 | Platform/Foundation | Done | Dashboard upgrade.
F-86 | S8 | Platform/Foundation | Done | List-page polish.
F-87 | S8 | Platform/Foundation | Done | **i18n: `dashboard.*` (welcome + stats + tasks + activity) + `topbar.*` (refresh / avatarLabel / signOut / sidebarToggle) added across en/si
F-88 | S8 | Platform/Foundation | Done | Form-page polish.
F-89 | S9 | M0/Survey | Done | Survey-wizard dotted-field-name bug fix.
F-90 | S9 | M3 Risk | Done | Module 4 data-collection research scaffolding.
F-91 | S10 | M0/Survey | Done | Sticky desktop sidebar + mobile drawer (hamburger trigger).
F-92 | S10 | M0/Survey | Done | `/admin/users` redesign
F-93 | S10 | M0/Survey | Done | Searchable multi-select Combobox primitive
F-94 | S10 | M0/Survey | Done | Admin-create-user endpoint + dialog.
F-95 | S10 | M0/Survey | Done | Two runtime bug fixes.
F-96 | S10 | M0/Survey | Done | Backend full CRUD for users.
F-97 | S10 | M0/Survey | Done | Backend full CRUD for regulations + soft-archive migration.
F-98 | S10 | M0/Survey | Done | Frontend full CRUD UI
F-99 | S10 | M0/Survey | Done | `<SurveyForm>` dotted-id leak (per-instrument awareness page).
F-100 | S11 | M0/Survey | Done | Backend admin survey-questions CRUD.
F-101 | S11 | M0/Survey | Done | `<QuestionForm>` + `/admin/questions/{list,new,[code]/edit}` pages.
F-102 | S11 | M0/Survey | Done | `<BranchingRulesEditor>` (Visual + JSON tabs).
F-103 | S11 | M0/Survey | Done | Regulation-anchored authoring wizard + LinkedQuestionsPanel.
F-104 | S11 | M0/Survey | Done | i18n: `questions.*`, `regulations.linkedQuestionsPanel.*`, `regulations.authoring.*`, `nav.adminQuestions`, `common.previous`.
F-105 | S11 | M2 Knowledge | Done | Sidebar entry `nav.adminQuestions` + deprecation note on the legacy M2 list.
F-106 | S12 | M0/Survey | Done | Branching validators (forward-ref / cycle / archived-target).
F-107 | S12 | M0/Survey | Done | Regulation-scoped flow.
F-108 | S12 | M0/Survey | Done | M:N junction `survey_question_regulations`.
F-109 | S12 | M0/Survey | Done | Backend i18n fallback.
F-110 | S12 | M0/Survey | Done | DB-driven per-instrument question fetch.
F-111 | S12 | M0/Survey | Done | Translation queue admin.
F-112 | S12 | M0/Survey | Done | Dashboard pending-regulations endpoint.
F-113 | S12 | M0/Survey | Done | Visual flow canvas.
F-114 | S12 | M0/Survey | Done | DB-driven per-module SME surveys.
F-115 | S12 | M0/Survey | Done | Two-tab surveys hub + regulation-scoped flow page.
F-116 | S12 | M0/Survey | Done | Dashboard widget — Regulations awaiting your assessment.
F-117 | S12 | M0/Survey | Done | Translations admin page + sidebar nav.
F-118 | S12 | M0/Survey | Done | Frontend types + API extensions.
F-119 | S13 | Platform/Foundation | Done | `<AnimatedLoadingSkeleton>` (`components/ui/`) — theme-adapted shadcn-pattern component.
F-120 | S13 | Platform/Foundation | Done | Streaming `loading.tsx` segments + skeleton wiring across the app.
F-121 | S13 | Platform/Foundation | Done | New SETUP doc `12_UI_Screens_and_Loading.md`.
F-122 | S13 | Platform/Foundation | Done | App-themed `<Pagination>` (`components/ui/`), wired into all eight admin tables.
F-123 | S13 | Platform/Foundation | Done | QA bug-fix batch.
F-124 | S14 | Platform/Foundation | Done | Audit-write consolidation + coverage closure.
F-125 | S14 | Platform/Foundation | Done | `AuthorshipMixin` — `created_by` / `updated_by` everywhere it matters.
F-126 | S14 | Platform/Foundation | Done | Admin Activity Log API.
F-127 | S14 | Platform/Foundation | Done | Admin Activity Log UI.
F-128 | S14 | Platform/Foundation | Done | Authorship footer on the admin edit pages.
F-129 | S15 | M3 Risk | Done | `survey_responses.linked_regulation_id` populated end-to-end.
F-130 | S15 | M3 Risk | Done | `meta.from_question_code` / `meta.from_rule` flow breadcrumb + `start_flow` fallback.
F-131 | S15 | M3 Risk | Done | Worked end-to-end scenario `VAT_SSCL_MERGE_2026` seeded.
F-132 | S15 | M3 Risk | Done | OQ32-class follow-up resolved — data-driven M3 question→risk-column mapping.
F-133 | S15 | M3 Risk | Done | Docs reconciliation + sidebar `/surveys` consolidation.
F-134 | S16 | M0/Survey | Done | `survey_limits` DB singleton + service.
F-135 | S16 | M0/Survey | Done | Admin survey-limits API + wiring.
F-136 | S16 | M0/Survey | Done | Admin settings frontend page.
F-137 | S16 | M0/Survey | Done | Sidebar nav + i18n for admin settings.
F-138 | S17 | M0/Survey | Done | `get_limits` catches `ProgrammingError` + rolls back session.
F-139 | S18 | Platform/Foundation | Done | Documentation sync across all affected MD files.
F-140 | S19 | M2 Knowledge | Done | M2/M3/M4 feature detail documentation sweep (SETUP + research).
F-141 | S19 | M2 Knowledge | Done | Tracker update — Session 19.
F-142 | S20 | M2 Knowledge | Done | Domain-based documentation restructuring (Session 20).
F-143 | S21 | Platform/Foundation | Done | M1 doc cleanup: section-header conformance + folder-path consistency sweep (Session 21).
F-144 | S22 | Platform/Foundation | Done | Backend seed refactor — demo dashboards populated on `make seed`.
F-145 | S23 | M1 Awareness | Done | M1 Phase 2 Step 2a — Scrapy gazette spider MVP (Session 23).
F-146 | S24 | Platform/Foundation | Done | `planned-for-devlopment/` folder convention + Step 2a setup doc + Vercel URLs noted (Session 24).
F-147 | S25 | Platform/Foundation | Done | Step 2a parse-bug fix + Step 2b planning docs (Session 25).
F-148 | S26 | M1 Awareness | Done | M1 Phase 2 Step 2b — Celery + Stage-B PDF extraction (Session 26).
F-149 | S28 | M1 Awareness | Done | M1 Phase 2 Step 2c — canonical extraction chain at `enigmatrix-ml/m1/extraction/` (Session 28).
F-150 | S29 | M0/Survey | Done | Auth pages split-panel UI (Session 29).
F-151 | S29 | M0/Survey | Done | M1 docs portal data consolidation (Session 29).
F-152 | S29 | M0/Survey | Done | Admin survey config: unified module option + multi-sector checkboxes — frontend only (Session 29).
F-153 | S30 | M1 Awareness | Done | M1 Phase 2 Step 2d — language detection + Wijesekara conversion + per-page OCR fallback (Session 30).
F-154 | S31 | M1 Awareness | Done | M1 Phase 2 Step 2e — Preprocessing chain at `enigmatrix-ml/m1/preprocessing/` (Session 31).
F-155 | S32 | M1 Awareness | Done | M1 Phase 2 Step 2f — Celery wiring + DB persistence for the Step-2e preprocessing chain (Session 32).
F-156 | S33 | Platform/Foundation | Done | M1 Phase 2 doc-only catch-up (Session 33).
F-157 | S34 | Platform/Foundation | Done | M1 Phase 2 cleanup (Session 34).
F-158 | S35 | Platform/Foundation | Done | Local-dev documentation lap (Session 35).
F-159 | S36 | Platform/Foundation | Done | Research-log portal (Session 36).
F-160 | S37 | M1 Awareness | Done | M1 Pipeline observability portal (Session 37).
F-161 | S38 | M1 Awareness | Done | Year + month-range scoped gazette extraction trigger (Session 38).
F-162 | S38 | M1 Awareness | Done | Celery eager-mode + pytest-asyncio session-loop fix for integration tests (Session 38).
F-163 | S39 | M1 Awareness | Done | Token-key sweep across 7 M1 admin pages (Session 39).
F-164 | S39 | M1 Awareness | Done | Gazette Extraction page UX enrichments — trigger history + summary card + per-row chips (Session 39).
F-165 | S40 | M1 Awareness | Done | M1 Pipeline in-page sub-nav: Gazette Extraction entry (Session 40).
F-166 | S40 | M1 Awareness | Done | Postgres connection-limit hotfix for the extract→preprocess fan-out (Session 40).
F-167 | S41 | M1 Awareness | Done | Pipeline-flow tiles surface a cumulative "reached" count (Session 41).
F-168 | S41 | M1 Awareness | Done | Aiven cloud-Postgres pool sizing fix (Session 41).
F-169 | S42 | M1 Awareness | Done | Date-range picker for Gazette Extraction (FE + BE, Session 42).
F-170 | S43 | Platform/Foundation | Done | Spider runtime fix — close spider when scope exhausted (Session 43).
F-171 | S44 | Platform/Foundation | Done | Theme polish (Session 44).
F-172 | S45 | M1 Awareness | Done | M1 pipeline page responsiveness v2 (Session 45).
F-173 | S46 | M1 Awareness | Done | Extraction running UX upgrade (Session 46).
F-174 | S47 | Platform/Foundation | Done | Frontend perf overhaul (Session 47).
F-175 | S49 | Platform/Foundation | Done | Live count polling for `summaryForResume` (Session 49).
F-176 | S49 | Platform/Foundation | Done | `SpiderResultCard` polished display (Session 49).
F-177 | S50 | Platform/Foundation | Done | Completeness check + re-fetch + spider EN→SI→TA fallback (Session 50).
F-178 | S51 | Platform/Foundation | Done | Completeness verify endpoint hardening (Session 51).
F-179 | S52 | Platform/Foundation | Done | AnimatedList component suite (Session 52).
F-180 | S52 | Platform/Foundation | Done | AnimatedItem applied to 6 list/card pages + sticky table headers across 13 table files (Session 52).
F-181 | S52 | Platform/Foundation | Done | FuzzyText component (Session 52).
F-182 | S52 | Platform/Foundation | Done | FuzzyText applied to 404, ComingSoon, Platform Map, Research Log (Session 52).
F-183 | S52 | Platform/Foundation | Done | Theme toggle: dropdown → single-click toggle button + View Transitions API circular reveal (Session 52).
F-184 | S53 | M1 Awareness | Done | M1 pipeline admin UX/UI audit — 14-finding report (Session 53).
F-185 | S54 | M1 Awareness | Done | Sticky M1 extraction inner sidebar (Session 54).
F-186 | S54 | M1 Awareness | Done | Resume/restart extraction for partial-state runs (Session 54).
F-187 | S54 | M1 Awareness | Done | Full extraction history table — replaces 5-item pill strip (Session 54).
F-188 | S54 | M1 Awareness | Done | Auto-scroll to progress panel on history row select (Session 54).
F-189 | S54 | M1 Awareness | Done | `m1_extraction_runs` DB model + Alembic migration (Session 54).
F-190 | S54 | M1 Awareness | Done | Backend: persist run on trigger + status sync on poll/cancel + `GET /runs` endpoint (Session 54).
F-191 | S54 | M1 Awareness | Done | Frontend: run history from `GET /runs` + localStorage write-through cache (Session 54).
F-192 | S54 | M1 Awareness | Done | SQLAlchemy QueuePool fix — `pool_size=3`, `max_overflow=5` (Session 54).
F-193 | S55 | Platform/Foundation | Done | Railway production deployment of `enigmatrix-backend` (Session 55).
F-194 | S55 | M1 Awareness | Done | Cancel + rollback admin endpoint — `POST /api/v1/admin/m1/extraction/cancel/{task_id}` (Session 55).
F-195 | S55 | M1 Awareness | Done | Cancel button + ConfirmDialog + inline result panel on extraction status card (Session 55).
F-196 | S55 | M1 Awareness | Done | Per-PDF metadata columns + extract-time population (migration `202605280001` + `pdf_metadata.py` helper) (Session 55).
F-197 | S55 | Platform/Foundation | Done | PDF Records browse-all admin page — `/admin/m1/pdf-records` + `GET /pdf-records` endpoint (Session 55).
F-198 | S55 | Platform/Foundation | Done | Cross-repo Stage 4 code-quality audit + three HIGH inline fixes (Session 55).
F-199 | S56 | M1 Awareness | Done | M1 raw PDF bulk extraction + classification — 800 PDFs across 11 batches (Session 56).
F-200 | S57 | M1 Awareness | Done | Slice 3 — backend-local XLSX parser wrapper + ML parser handle close (Session 57).
F-201 | S57 | M1 Awareness | Done | Slice 3 — reproducible 5-row M1 master xlsx test fixture (Session 57).
F-202 | S57 | M1 Awareness | Done | Slice 3 — parser unit test suite (Session 57).
F-203 | S57 | M1 Awareness | In Progress | Slice 3 — upload integration test suite (Session 57).
F-204 | S57 | M1 Awareness | Done | Slice 3 — `/admin/m1/datasets/new` create page + form component (Session 57).
F-205 | S57 | M1 Awareness | In Progress | Slice 3 — Playwright E2E spec for create/upload/promote/idempotency (Session 57).
F-206 | S58 | M1 Awareness | Done | Datasets restructure — i18n migration m1Datasets.* → datasets.m1.* + new datasets.hub.* namespace (Session 58).
F-207 | S58 | M1 Awareness | Done | Datasets restructure — moved M1 pages under /admin/datasets/m1/* + new hub at /admin/datasets (Session 58).
F-224 | S62 | M1 Awareness | Unknown | Phase 3e — evaluation + slice analysis + baselines (Session 62, planned).
F-225 | S62 | M1 Awareness | In Progress | Phase 3f — ONNX export + `classify_gazette` inference wiring + deploy (Session 62, planned).
F-226 | S63 | M1 Awareness | Done | Phase 3d — `enigmatrix-ml/m1/model/` classifier scaffold (Session 63).
F-227 | S64 | M1 Awareness | Done | Phase 3e — evaluation + baselines (`m1/model/eval.py` + `baselines.py`) (Session 64).
F-228 | S65 | M1 Awareness | Done | Phase 3f — inference wiring (ONNX export + `classify_gazette`) (Session 65).

## Manual Test Plan
Manual Test Plan — flows, expected outcomes & next steps
One test per system segment (done + pending + not-started). "Runnable" = can you run it today. Use with the setup runbook in the HTML dossier.
Runnable now | 8
Pending (needs prereq) | 6
Not built yet | 5
Test ID | Phase / Segment | Feature | Why (objective) | Preconditions | Test steps (the flow) | Expected outcome | Runnable | Status | What next
T-01 | Phase 1 · Regulation CRUD | Admin regulation CRUD + verify | Confirm admins can enter & expert-verify regulations — the ground truth the survey and classifier rely on. | Backend + frontend running; admin@enigmatrix.lk seeded. | 1. Log in as admin. 2. Go to /admin/regulations → New; fill title, gazette date, category; Save. 3. Open the detail page → click Verify (and try Bulk-verify). 4. Open the admin Activity Log. | Regulation appears in the list; status shows verified; an audit_log row is written for the mutation. | Now | Pass (verify) | —
T-02 | Phase 1 · Awareness survey | M0 awareness survey (EN/SI/TA) | The awareness instrument is RQ1's data-collection tool — must work in all three languages and store responses. | Seeded DB; a demo SME user. | 1. Log in as a demo SME. 2. Open /surveys/awareness; switch language EN→SI→TA. 3. Answer the 12 questions; submit. 4. As admin, open /admin/surveys/awareness/responses. | Response is saved and visible in the admin table; all three language variants render correctly. | Now | Pass (verify) | —
T-03 | Phase 2 · 2a Spider | Scrapy gazette spider | Automated gazette discovery is the first link in measuring the awareness lag. | Redis + backend up; storage/ writable. | 1. Run `uv run scrapy crawl gazette_spider` (or Admin → /admin/m1/pipeline → trigger extraction with a date range). 2. Watch the run card / logs. | N PDFs land in storage/m1/raw/; N new m1_regulations rows at status='ingested' with gazette_number set. | Now | Pass (verify) | —
T-04 | Phase 2 · 2b–2f Extract→Preprocess | extract_gazette + preprocess_gazette | PDFs must become clean, chunked text with extracted metadata for the classifier and lag analysis. | Celery worker running; at least one row at status='ingested'. | 1. Start `uv run celery -A app.celery_config worker -l info`. 2. Let extract_gazette run; it chains preprocess_gazette. 3. Query the row's status + fields. | status flows ingested→extracted→preprocessed; raw_text + cleaned_text populated; gazette_number / effective_date / penalties / principal_act extracted. | Now | Pass (verify) | —
T-05 | Phase 2 · 2c Extraction chain | ml/m1/extraction unit tests | The multi-engine PDF routing must be correct before we trust extracted text. | cd enigmatrix-ml; extraction deps installed. | 1. `uv run pytest tests/m1/extraction -v`. | Extraction tests pass (PDF-type classifier shape/determinism, engine routing). CER/50-PDF-audit tests skip until a gold corpus exists. | Now | Partial (gold corpus pending) | Populate the 50-PDF audit + OCR-gold corpus.
T-06 | Phase 2 · 2d Language/Wijesekara | language_detection + wijesekara | SL gazettes mix EN/SI/TA and legacy Sinhala fonts — both must normalise or RQ2 (SI/TA F1) fails. | fastText lid.176.bin downloaded. | 1. Run the fastText detector on an EN/SI/TA sample. 2. Run Wijesekara conversion on a pre-2010 Sinhala doc. 3. Inspect the output text. | Language correctly detected per line; legacy Sinhala converts to clean Unicode (no (cid:…) glyphs). | Now | Partial (100-doc gold pending) | Build the 100-doc lang + Wijesekara gold sets.
T-07 | Phase 2 · Upgrade | Dataset registry + measurement engine | Extraction-quality claims must be measurable vs a golden ground truth (research rigor). | Backend up; a golden xlsx. | 1. /admin/datasets/m1 → Create dataset → upload golden xlsx (sealed version). 2. Run an extraction with a profile. 3. Run a measurement (baseline vs candidate). 4. Open the comparison view. | A measurement run with per-field scores + completeness; the comparison UI renders metrics and the v1→v2 overlap badge. | Now | Pass (verify) | —
T-08 | Phase 3 · 3a Annotation setup | Label Studio + calibration (κ) | Annotators must agree (Cohen's κ≥0.80) before labelling at scale, or the gold set is noisy. | Label Studio installed; 2 annotators. | 1. Install label-studio; paste research/data/label_studio_config.xml. 2. Import calibration_set_v1.csv (20 docs). 3. Both annotators label the 20; compute κ vs expert labels. | κ≥0.80 on first attempt (≥60% pass); if below, refine the edge-case guidance and re-run. | Pending | Pending | Recruit 2 annotators; run the calibration round.
T-09 | Phase 3 · 3b Sampling | sample_for_labeling.py | Stratified + diverse + uncertainty sampling reaches high F1 with fewer labels than random. | cd enigmatrix-ml. | 1. `python scripts/sample_for_labeling.py --demo --dry-run` (counts). 2. `python scripts/sample_for_labeling.py --demo` (writes batch). | batch_01.csv (200 rows = 150 stratified + 40 k-means + 10 minority) + provenance JSON; ≥3 languages. | Now | Pass (demo) | Run `make labeling-batch` against the prod DB for the real batch.
T-10 | Phase 3 · 3c Gold labels | Annotate to ≥800 | This is the classifier's training data — the single hard gate for the RQ1 result. | 3a calibration passed; real batch produced. | 1. `make labeling-batch` (prod DB) → Label Studio. 2. Label; iterate active-learning batches (uncertainty first) with 15% dual-annotation. 3. Export gold_standard.csv; build temporal split. | ≥800 labels, ≥50/category, dual-annotated κ≥0.75; train/val/test.parquet with no date leakage. | Pending | Not built | Execute 3a→3c; ~6 weeks of labelling.
T-11 | Phase 3 · 3d Model/train | m1/model tests + training | Verify the classifier code is correct and the training loop runs to the F1 gate. | cd enigmatrix-ml; `uv sync --extra training`; gold split present (from 3c). | 1. `uv run pytest tests/m1/model -v` (labels/data pass now; architecture is slow/skips without torch). 2. Mini-smoke: train LoRA r=8, 1 epoch on the first 300 labels. 3. Full: `python -m m1.model.train_xlmr --data datasets/m1_regulations --seeds 42 1 2 --fp16 --out storage/models/m1/xlmr_lora_v1`. | label/data tests pass now; mini-smoke writes a model_registry.json; full run reaches 3-seed macro-F1≥0.92 (EN≥0.93/SI≥0.88/TA≥0.86). | Pending | Partial (label/data tests pass now) | After 3c: install training extra + run on a GPU.
T-12 | Phase 3 · 3e Eval | eval.py + baselines.py | Aggregate F1 can hide a weak language/quarter; the baseline comparison is itself a finding. | A trained model + test.parquet. | 1. `python -m m1.model.eval --model … --test … --report …`. 2. `python -m m1.model.baselines --data … --report …`. 3. Read metrics.json + baselines.json. | metrics.json: macro-F1≥0.92, per-language gates met, no slice cliff >8pp; baselines table produced; error_analysis_topwrong.csv saved. | Pending | Pending | Run after 3d; eval-helper unit tests already pass.
T-13 | Phase 3 · 3f Inference | classify_gazette end-to-end | Every preprocessed gazette must auto-classify into its concept, low-confidence routed to review. | Migration applied; ONNX model exported + M1_MODEL_ONNX_DIR set. | 1. `alembic upgrade head` (adds classifier_confidence + classified_at). 2. `python -m m1.model.export_onnx --int8`; set M1_MODEL_ONNX_DIR. 3. Ensure a 'preprocessed' row; worker runs classify_gazette (or preprocess chains it). 4. Run `pytest app/tests/integration/test_celery_classify_gazette.py`. | status preprocessed→classified; change_category + classifier_confidence + classified_at set; confidence<0.55 flagged for the review queue. | Pending | Pending | Run after 3d/3e; wiring already in place.
T-14 | Phase 4 · 4a Watchers | portal/rss watchers | The information lag can only be measured if each downstream appearance is timestamped. | portal_watcher/rss_watcher built; m1_sources populated. | 1. Build the watcher tasks over the 15-source registry. 2. Run on Beat (every 2h). 3. Query m1_propagation_events. | One row per (regulation × channel) with first_seen_at + match_method/confidence. | Not built | Not built | Build 4a (Phase 4).
T-15 | Phase 4 · 4b Alerts | alert_dispatch | The alert system is Objective 1's deliverable and the DiD treatment arm (F6). | alert_dispatch built; SendGrid/Twilio keys. | 1. Build alert_dispatch (batched, rate-limit-aware). 2. Trigger for a high-fan-out regulation (≥500 SMEs). 3. Re-trigger to test idempotency. | Alerts deliver ≤1h p99; exactly once per (regulation, sme, channel). | Not built | Not built | Build 4b (Phase 4).
T-16 | Phase 4 · 4c Analytics | nightly refresh + drift | Keeps lag analytics fresh and catches model drift for retraining. | analytics task built. | 1. Build the nightly analytics task. 2. Run it; inject synthetic drift. 3. Check the lag-summary view + drift trigger. | View refreshes nightly; KL-divergence drift trigger fires on synthetic drift. | Not built | Not built | Build 4c (Phase 4).
T-17 | Phase 5 · 5a Survey | SME survey deployment | Stage-C awareness timestamp turns propagation data into a measured lag (RQ3). | /portal/m1/survey wired; partners engaged. | 1. Wire the survey to the 9-regulation selection SQL. 2. Distribute via NEDA/Chamber; ethics/IRB. 3. Track responses by sector. | ≥100 unique SME respondents, ≥10 per sector, all 9 regulations answered. | Pending | Pending | Deployment + outreach + ethics approval.
T-18 | Phase 5 · 5b Findings | F1–F6 notebooks | The empirical answer to RQ1/RQ3/RQ4 — the thesis contribution. | Propagation + survey data present. | 1. Build research/notebooks/findings_*.ipynb (write preregistration first). 2. Run against a production replica. 3. Report each finding. | F1–F6 each with median + bootstrap CI + statistical test (Kruskal–Wallis / Mann-Whitney / DiD). | Not built | Not built | Build 5b after Phase 4 data flows.
T-19 | Phase 5 · 5c Retraining | retrain + rollback | Sustains model quality as the corpus grows. | retrain.py + m1_retraining_runs built. | 1. Build retrain.py + canary helper. 2. Quarterly dry-run on staging. 3. Inject a synthetic F1 drop. | Dry-run completes end-to-end; auto-rollback fires on the F1 drop. | Not built | Not built | Build 5c (Phase 5).

## Roadmap vs Actual
Phase | Step | Planned deliverable | Definition of Done | Status | Evidence (F-id / Session) | Notes | Score
Phase 1 — Foundation | — | Admin regulation CRUD + verify, audit log, unified M1→M2→M3 survey engine, 5 seed regs | Shipped & inherited | Done | F-65..F-97 (S6–22) | Baseline; not rebuilt. | 1
Phase 2 — Ingest+Extract | 2a Scrapy gazette spider | scraper/spiders/gazette_spider.py → PDFs + rows status=ingested | N PDFs + N ingested rows | Done | F-144/145 (S23); +weekly/acts/bills (S38) | 4 spiders + sources hub. | 1
Phase 2 — Ingest+Extract | 2b Celery wiring + extract | gazette_scraper + extract_gazette tasks → status=extracted | row→extracted | Done | F-148 (S26) |  | 1
Phase 2 — Ingest+Extract | 2c PDF classifier + extraction chain | ml/m1/extraction (pdf_classifier, extractors, ocr) | ≥95% classify; CER≤10% | Done | F-149 (S28) | Harness shipped; CER gold corpus pending. | 1
Phase 2 — Ingest+Extract | 2d Language detection + Wijesekara | fastText lid.176 + Wijesekara conversion | ≥95% lang accuracy | Done | F-153 (S30) |  | 1
Phase 2 — Ingest+Extract | 2e Preprocessing chain | cleaning + metadata + chunking | cleaned+metadata+chunked | Done | F-154 (S31) |  | 1
Phase 2 — Ingest+Extract | 2f DB persistence | preprocess_gazette task → status=preprocessed | row→preprocessed | Done | F-155 (S32) |  | 1
Phase 2 — Ingest+Extract | Upgrade (slices 1–9) | Datasets registry+versioning, extraction profiles, measurement engine | Measure extraction quality | Done | F-200..F-215 (S57–60) | Beyond original roadmap. | 1
Phase 3 — Annotation+Classify | 3a Label Studio + calibration | LS config XML + 20-doc calibration set | Annotators; κ≥0.80 | In Progress | F-216/217 (S61) | Config+calib built; annotators not recruited. | 0.5
Phase 3 — Annotation+Classify | 3b Sample first 300 | samplers.py + sample_for_labeling.py + batch_01 | batch_01 (200 docs) | Done | F-218/219/220 (S61) | 200-row demo; real batch pending prod DB. | 1
Phase 3 — Annotation+Classify | 3c Iterate to 800 labels (AL) | 800 gold labels via active learning | 800 gold, κ≥0.75 | Not Started | planned F-222 (S62) | Needs human annotators. | 0
Phase 3 — Annotation+Classify | 3d Train XLM-R + LoRA | m1/model (architecture, train_xlmr) | 3-seed macro-F1≥0.92 | In Progress | F-226 (S63); F-223 | Scaffold done; train pending gold+GPU. | 0.5
Phase 3 — Annotation+Classify | 3e Eval + slice analysis | m1/model/eval.py + baselines.py | No slice cliff >8pp | In Progress | F-227 (S64); F-224 | Scaffold done; run pending trained model. | 0.5
Phase 3 — Annotation+Classify | 3f ONNX export + deploy + wiring | export_onnx + inference + classify_gazette task | INT8 within 1.5pp; p95≤2s | In Progress | F-228 (S65); F-225 | Wiring done; export/deploy pending model. | 0.5
Phase 4 — Schedulers+Alerts+Lag | 4a Portal + RSS watchers | portal_watcher + rss_watcher → m1_propagation_events | Watchers write lag events | Not Started | — | RQ3/RQ4 lag data source. | 0
Phase 4 — Schedulers+Alerts+Lag | 4b Alert dispatch | alert_dispatch (SendGrid + Twilio) | ≤1h p99; idempotent | Not Started | — |  | 0
Phase 4 — Schedulers+Alerts+Lag | 4c Nightly view refresh + drift | analytics task + KL-divergence drift | Drift fires; SLA dashboard | Not Started | — |  | 0
Phase 5 — Findings+Survey | 5a SME survey deployment | wire /portal/m1/survey; partner outreach | ≥100 SME respondents | In Progress | M0 survey F-33–36 | Instrument live; lag-tied deployment pending. | 0.5
Phase 5 — Findings+Survey | 5b F1–F6 findings notebooks | research/notebooks/findings_*.ipynb | median+CI+test each | Not Started | — | The empirical RQ1 answer. | 0
Phase 5 — Findings+Survey | 5c Retraining cadence + rollback | retrain.py + canary + m1_retraining_runs | Dry-run + auto-rollback | Not Started | — |  | 0

## Status Rollup
Status Rollup
Status | Count | % of features
Done | 204 | 96.23%
In Progress | 4 | 1.887%
Not Started | 3 | 1.415%
Blocked | 0 | 0%
Dropped | 0 | 0%
Unknown | 1 | 0.4717%
TOTAL | 212 | 100%
Area / Module | Features | Done | % Done
M0/Survey | 58 | 55 | 94.83%
M1 Awareness | 50 | 46 | 92%
M2 Knowledge | 19 | 19 | 100%
M3 Risk | 11 | 10 | 90.91%
Platform/Foundation | 74 | 74 | 100%

## Gaps & Next
Gaps & Next Actions — what remains
Derived from roadmap steps not yet Done + open feature statuses. Ordered by the critical path.
Priority | Item | Status | What it unlocks | Next action
P0 | Fix /admin/m1/pipeline/recent 503 (F-184) + reconcile F1 gate (0.80 vs 0.92) | In Progress | Demo integrity; correct thesis bar | Fix RSC 503; grep-replace 0.80→0.92 across BUILD_11/roadmap.
P1 | 3c — Annotate to ≥800 gold labels (κ≥0.75) | Not Started | RQ1 classifier training data | Recruit 2 annotators; make labeling-batch; calibrate; active-learning to 800.
P1 | 3d — Train XLM-R+LoRA (scaffold ready) | In Progress | RQ1 macro-F1≥0.92 result | After gold: uv sync --extra training; python -m m1.model.train_xlmr on GPU.
P1 | 3e — Eval + baselines (scaffold ready) | In Progress | Proves RQ1 + baseline finding | python -m m1.model.eval + baselines on trained model.
P1 | 3f — ONNX export + deploy (wiring ready) | In Progress | Operational classifier in pipeline | alembic upgrade head; export_onnx --int8; set M1_MODEL_ONNX_DIR; deploy.
P2 | 4a — Portal + RSS watchers → m1_propagation_events | Not Started | RQ3/RQ4 lag dataset | Build portal_watcher + rss_watcher over 15 sources; Celery Beat.
P2 | 4b — Alert dispatch (SendGrid/Twilio) | Not Started | Objective-1 alert system (≤24h) | Build alert_dispatch; idempotent per (reg,sme,channel).
P2 | 4c — Nightly view refresh + drift | Not Started | Lag analytics + monitoring | Build analytics task; KL-divergence drift.
P3 | 5a — SME survey deployment (≥100 respondents) | In Progress | RQ3 awareness-lag data | Wire /portal/m1/survey; NEDA/Chamber outreach; ethics/IRB.
P3 | 5b — F1–F6 findings notebooks | Not Started | The empirical thesis result | Build 4 findings_*.ipynb; preregistration first.
P3 | 5c — Retraining cadence + auto-rollback | Not Started | Sustainable model ops | retrain.py + canary + m1_retraining_runs.
Data | SI/TA raw_text (cid:) re-extraction | Not Started | RQ2 (SI/TA F1) integrity | Re-extract SI/TA via OCR+Wijesekara before building gold text.