## Summary
Enigmatrix — Module 1 Development Evaluation
Whole-project build vs the 16_M1_Development_Roadmap · owner Mohamed M.R.I (215075J) · generated 2026-06-30 (through Session 69, F-238)
Metric | Value | Notes
Total features tracked | 215 | F-01 … F-238
Features Done | 205 | done
Features In Progress | 6 | scaffolded/partial
Features Not Started | 3 | planned
Feature completion % | 95.35% | Done / total
Roadmap completion (weighted) | 68.42% | Done=1, In Progress=0.5
Manual tests runnable now | 7 | flows runnable today
Phase 1 | 100% | complete
Phase 2 | 100% | complete (+upgrade)
Phase 3 | 50% | model/eval/wiring built; 3c pending
Phase 4 | 50% | 4a/4b/4c code-complete
Phase 5 | 50% | 5b built; survey+5c pending
Verdict
Phases 1–2 shipped in production. Phase 3 classifier is code-complete (model, eval, ONNX inference wiring) pending gold labels (3c) + a GPU training run. Phase 4 is code-complete end-to-end — watchers → propagation events (4a), sector-matched alerts + a public/SME website /alerts feed (4b), and nightly lag materialized views + KL drift (4c) — pending migrations + live data. Phase 5 has the F1–F6 findings notebooks built (5b, on a synthetic demo) pending the survey (5a) + real data. Remaining pure-code piece: 5c retraining/rollback.

## Feature Register
ID | Session | Area | Status | Feature
F-01 | — | Platform/Foundation | Done | Monorepo scaffold (`backend/ frontend/ ml/ infra/ docs/tracker/ scripts/`) + root configs ¦ 🟢 ¦ `BUILD_02 §1–§6` ¦ `tree -L 2` matches §1 layout ¦
F-02 | — | Platform/Foundation | Done | Dev infrastructure: `docker-compose.dev.yml` + `infra/postgres/init.sql` ¦ 🟢 ¦ `BUILD_04 §2` ¦ `make up` brings Postgres healthy ¦
F-03 | — | Platform/Foundation | Done | `.gitignore`, `.env.example`, `Makefile`, root `README.md`, pre-commit ¦ 🟢 ¦ `BUILD_01 §6` ¦ `pre-commit install` succeeds ¦
F-04 | — | Platform/Foundation | Done | Tracker bootstrap (`docs/tracker/{README,FEATURES,SESSIONS,CHANGES}.md`) ¦ 🟢 ¦ this plan ¦ All four files exist ¦
F-05 | — | Platform/Foundation | Done | FastAPI app: `main.py`, `settings.py`, `logging_config.py`, `exceptions.py`, `deps.py` ¦ 🟢 ¦ `BUILD_03 §3–§7` ¦ `GET /health` returns 200 (verified on
F-06 | — | Platform/Foundation | Done | Pydantic v2 settings with `DATABASE_URL` (asyncpg) + `JWT_SECRET` + `CORS_ORIGINS` ¦ 🟢 ¦ `BUILD_03 §3` ¦ `app/settings.py` boots with `.env` ¦
F-07 | — | Platform/Foundation | Done | SQLAlchemy 2.0 async session + `DeclarativeBase` + `TimestampMixin` ¦ 🟢 ¦ `BUILD_04 §3` ¦ `db_session` fixture in `conftest.py` validates round-trip ¦
F-08 | — | M1 Awareness | Done | ORM models: `User`, `SMEProfile`, `SurveyResponse`, `AuditLog` ¦ 🟢 ¦ `BUILD_04 §5` + `research/06 §4` ¦ `python -m compileall app` clean; models regis
F-09 | — | Platform/Foundation | Done | Alembic init + initial migration (`202605080001_initial_schema.py`) ¦ 🟢 ¦ `BUILD_04 §4` ¦ `alembic upgrade head` succeeds on fresh DB (verified at run
F-10 | — | Platform/Foundation | Done | Auth: `core/security.py` (bcrypt + HS256 JWT access/refresh) ¦ 🟢 ¦ `BUILD_06 §2` ¦ `tests/unit/test_security.py` round-trips access + refresh ¦
F-11 | — | Platform/Foundation | Done | Auth service + schemas + router (`/auth/register`, `/auth/login`, `/auth/refresh`) ¦ 🟢 ¦ `BUILD_06 §3–§5` ¦ Integration test passes register + login ¦
F-12 | — | M1 Awareness | Done | RBAC: `get_current_user`, `require_admin`, `require_annotator` deps ¦ 🟢 ¦ `BUILD_03 §6` + `BUILD_06 §6` ¦ Integration test asserts SME → 403 on admin
F-13 | — | Platform/Foundation | Done | Inbound rate limit on `/auth/login` and `/auth/register` (slowapi) ¦ 🟢 ¦ `BUILD_06 §9` ¦ `core/rate_limit.py` wired in `main.py`; auth router decorate
F-14 | — | M1 Awareness | Done | `users.py` router: `GET /api/v1/users/me`, admin-only `GET /api/v1/users` ¦ 🟢 ¦ `BUILD_03 §13` ¦ `api/v1/users.py` returns user + profile ¦
F-15 | — | M0/Survey | Done | `surveys.py` router: `POST /surveys/{instrument}/submit`, `GET /surveys/{instrument}/responses` (admin) ¦ 🟢 ¦ this plan ¦ Integration test exercises b
F-16 | — | Platform/Foundation | Done | Audit-log writes on auth events ¦ 🟢 ¦ `BUILD_06 §10` ¦ `auth_service` writes `auth.register`, `auth.login.success/failure`, `auth.refresh` rows ¦
F-17 | — | M3 Risk | Done | Module-router 501 stubs (`regulations`, `qa`, `risk`, `verify`) ¦ 🟢 ¦ this plan ¦ Integration test asserts each returns 501 + `code: not_implemented`
F-18 | — | M1 Awareness | Done | `seed_dev.py`: admin + annotator + sample SME ¦ 🟢 ¦ `BUILD_04 §8` ¦ `make seed` is idempotent ¦
F-19 | — | Platform/Foundation | Done | Next.js 14 app (App Router, TS, Tailwind) ¦ 🟢 ¦ `BUILD_05 §1` ¦ `package.json` + `next.config.mjs` + `app/layout.tsx` present ¦
F-20 | — | M1 Awareness | Done | shadcn-pattern primitives: button, input, label, card, badge, alert, skeleton, dropdown-menu, select, radio-group, checkbox, table, toaster, textarea
F-21 | — | Platform/Foundation | Done | Domain-tuned theme tokens (trust-blue 217 91% 50% + amber 38 92% 50%) for light + dark ¦ 🟢 ¦ this plan + `BUILD_05 §2` ¦ `app/globals.css` defines all
F-22 | — | Platform/Foundation | Done | `next-themes` light/dark/system toggle in topbar ¦ 🟢 ¦ this plan ¦ `components/layout/theme-toggle.tsx` mounted in `Topbar` ¦
F-23 | — | Platform/Foundation | Done | Multilingual fonts via `next/font` (Inter + Noto Sans Sinhala + Noto Sans Tamil) ¦ 🟢 ¦ `BUILD_05 §3` ¦ `app/layout.tsx` registers all three font CSS v
F-24 | — | Platform/Foundation | Done | `next-intl` with `en/si/ta`; locale switcher in topbar ¦ 🟢 ¦ `BUILD_05 §4` ¦ `i18n.ts` + 3 messages files; `LocaleSwitcher` writes `NEXT_LOCALE` cooki
F-25 | — | M0/Survey | Done | API client (`lib/api/client.ts`) with `ApiError` + bearer token plumb ¦ 🟢 ¦ `BUILD_05 §5` ¦ `lib/api/{client,auth,surveys,users}.ts` ¦
F-26 | — | Platform/Foundation | Done | `lib/auth/{session,roles}.ts` — server-side `requireUser()` / `requireRole()` ¦ 🟢 ¦ `BUILD_06 §8` ¦ `(app)` and `(admin)` layouts call them ¦
F-27 | — | Platform/Foundation | Done | TanStack Query + theme provider in `components/providers.tsx` ¦ 🟢 ¦ `BUILD_05 §9` ¦ Query client mounted under `ThemeProvider` ¦
F-28 | — | Platform/Foundation | Done | `/login` page (zod + react-hook-form + shadcn) ¦ 🟢 ¦ `BUILD_06 §8` ¦ Posts to backend, calls `/api/auth/establish`, redirects to `next` ¦
F-29 | — | M1 Awareness | Done | `/register` page (email + password + SME profile fields) ¦ 🟢 ¦ `BUILD_06 §3` ¦ Creates user + profile, then auto-logs-in ¦
F-30 | — | Platform/Foundation | Done | Cookie route handlers: `/api/auth/establish`, `/api/auth/token`, `/api/auth/logout` ¦ 🟢 ¦ `BUILD_06 §8` ¦ HTTP-only cookies set on login, cleared on l
F-31 | — | Platform/Foundation | Done | Auth-guarded `(app)` layout + admin-guarded `(admin)` layout + middleware fast-path ¦ 🟢 ¦ `BUILD_05 §7` ¦ `middleware.ts` redirects unauth'd users; `r
F-32 | — | Platform/Foundation | Done | Topbar with role badge + email + theme + locale + logout ¦ 🟢 ¦ this plan ¦ `components/layout/topbar.tsx` ¦
F-33 | — | M0/Survey | Done | Awareness question bank `lib/surveys/awareness.ts` (12 items) ¦ 🟢 ¦ `research/08` + plan ¦ All 6 question kinds covered (single, multi, likert, date,
F-34 | — | M0/Survey | Done | Reusable `SurveyForm` + `QuestionRenderer` for all 6 kinds ¦ 🟢 ¦ `BUILD_05 §11` ¦ Each kind validates + serialises to backend `SurveyAnswerIn` ¦
F-35 | — | M0/Survey | Done | `/surveys/awareness` page submits to `POST /surveys/awareness/submit` ¦ 🟢 ¦ this plan ¦ On success, router pushes to `/surveys/awareness/thank-you` ¦
F-36 | — | M0/Survey | Done | `/surveys/awareness/thank-you` confirmation ¦ 🟢 ¦ this plan ¦ Renders w/ "Back to dashboard" CTA ¦
F-37 | — | M0/Survey | Done | Admin response list `/admin/surveys/awareness` (table + total + pagination params) ¦ 🟢 ¦ this plan ¦ shadcn `Table` lists submissions grouped by (sme,
F-38 | — | M0/Survey | Done | Admin user list `/admin/users` (read-only, role badges) ¦ 🟢 ¦ this plan ¦ shadcn `Table` shows email + role badge + sector + region ¦
F-39 | — | M3 Risk | Done | "Coming soon" stubs for `/regulations`, `/qa`, `/verify`, `/risk` ¦ 🟢 ¦ `BUILD_05 §10` ¦ Each renders `<ComingSoon>` with the relevant `BUILD_NN` refe
F-40 | — | M0/Survey | Done | Backend integration test `test_survey_flow.py` (httpx + Postgres testcontainer) ¦ 🟢 ¦ plan + `BUILD_15 §6` ¦ Two test cases: full register/login/submi
F-41 | — | Platform/Foundation | Done | Backend unit tests for `core/security` (bcrypt + JWT round-trip) ¦ 🟢 ¦ this plan ¦ `tests/unit/test_security.py` ¦
F-42 | — | M0/Survey | Done | Playwright E2E `auth_survey_admin.spec.ts` ¦ 🟢 (script ready) ¦ plan ¦ Runs on `make dev-frontend` + seeded backend; needs runtime verification once `
F-43 | S3 | Platform/Foundation | Done | Now 12 files
F-44 | — | M2 Knowledge | Done | Backend schema: `regulatory_domains`, `sectors`, `m2_questions`, `m2_knowledge_scores`, `m3_compliance_history`, `m3_behavioural_signals` + `survey_re
F-45 | — | M2 Knowledge | Done | M2 question bank seed (`seed_m23_questions.py`) — 9 domains + 12 sectors + 40 canonical questions verbatim from `module_2_and_3` PART A ¦ 🟢 ¦ this pla
F-46 | — | M2 Knowledge | Done | Cross-module-linkage rules (`m2_linkage_rules.py`) — awareness → M2 question selection ¦ 🟢 ¦ this plan ¦ Rule fires on `awareness.v1.q04 = no` forcing
F-47 | — | M2 Knowledge | Done | M2 scoring engine (`m2_scoring.py`) — mcq, scenario, numeric, ordered_steps with partial-credit, open with element-matching ¦ 🟢 ¦ this plan ¦ `test_m2
F-48 | — | M2 Knowledge | Done | M2 service: `questions_for_sme`, scoring on submit, `recompute_knowledge_score` cache write ¦ 🟢 ¦ this plan ¦ `test_m2_flow.py` asserts `is_correct` p
F-49 | — | M2 Knowledge | Done | M3 service: history submit, behavioural submit, combined `risk-signals` view (BUILD_00 contract) ¦ 🟢 ¦ this plan ¦ `test_m3_flow.py` asserts the combi
F-50 | — | M2 Knowledge | Done | M2 + M3 routers (`/api/v1/m2/*`, `/api/v1/m3/*`); `SupportedInstrument` extended to `["awareness","knowledge","vulnerability"]` ¦ 🟢 ¦ this plan ¦ Open
F-51 | — | M2 Knowledge | Done | Frontend conditional questions: shared `types.ts`, `dependsOn` evaluator, renderer `useWatch`, submit-time stripping ¦ 🟢 ¦ this plan ¦ M3 vulnerabilit
F-52 | — | M2 Knowledge | Done | Frontend SME pages: Surveys hub `/regulations`, Knowledge survey + thank-you, Vulnerability survey + thank-you, Risk read-only `/risk` ¦ 🟢 ¦ this plan
F-53 | — | M2 Knowledge | Done | Frontend admin pages: M2 question bank with inline Verify, M2 scores, M3 risk-signals ¦ 🟢 ¦ this plan ¦ Admin `/admin/m2/questions` Verify action sets
F-54 | — | M2 Knowledge | Done | UX polish: sticky `SurveyProgress` (visible-only denominator), `useAutosave` to localStorage every 10s with Resume banner, `SurveyErrorSummary` with a
F-55 | — | M2 Knowledge | Done | i18n parity: en/si/ta all carry the new `surveys.hub`, `surveys.knowledgeTitle`, `risk`, `admin` keys (116 keys each) ¦ 🟢 ¦ this plan ¦ JSON key count
F-56 | — | M2 Knowledge | Done | Backend integration tests (`test_m2_flow.py`, `test_m3_flow.py`) + unit (`test_m2_scoring.py`) + Playwright (`surveys_knowledge_vulnerability.spec.ts`
F-57 | S5 | Platform/Foundation | Done | bcrypt pin `>=4.0,<4.1` in `backend/pyproject.toml` — stops the recurring passlib `__about__` AttributeError + 72-byte ValueError on hash. ¦ 🟢 ¦ sessi
F-58 | S5 | Platform/Foundation | Done | Defensive 72-byte UTF-8 truncation in `app/core/security.py` — both `hash_password` and `verify_password` now route every secret through `_truncate()`
F-59 | S5 | Platform/Foundation | Done | `.env.example` `CORS_ORIGINS` ships in JSON-array form (`["http://localhost:3000"]`) with an inline comment. ¦ 🟢 ¦ session 5 (Pydantic Settings v2.1+
F-60 | S5 | Platform/Foundation | Done | `docs/SETUP/09_Troubleshooting.md` updated: entry 9 rewritten with the actual root cause + actual fix; new 9b (long unicode passwords), 25b (missing `
F-61 | S5 | Platform/Foundation | Done | CORS preflight 400 fix in `app/main.py` — strip trailing slash from every entry before passing to `CORSMiddleware`. Pydantic v2's `AnyHttpUrl.__str__`
F-62 | S5 | Platform/Foundation | Done | Auth diagnostics + DB-inspection toolkit. New `make doctor` (`backend/app/scripts/doctor.py`) checks bcrypt version, hash round-trip, and the seeded u
F-63 | S5 | M0/Survey | Done | App-Router parallel-pages collision fix. The admin awareness response list was at `/admin/surveys/awareness`, but Next.js strips route groups from URL
F-64 | S5 | M0/Survey | Done | `useAutosave` no longer reaches into `useFormContext()` — the call ran before `<FormProvider>` mounted, returning `null` and crashing every survey pag
F-65 | S6 | M0/Survey | Done | Unified `survey_questions` schema (rename of `m2_questions` + `module_number`/`linked_regulation_id`/`next_question_rules`/`is_required`/`instrument_s
F-66 | S6 | M3 Risk | Done | Idempotent seed scripts: `seed_regulations` (5 canonical regs), `seed_awareness_questions` (12 M0 with cross-module rules), `seed_vulnerability_questi
F-67 | S6 | M0/Survey | Done | Flow engine (`survey_question_service`): `start_flow`, `next_question`, `_resolve_rule` (predicates `answer_eq` / `answer_in` / `answer_lt` / `answer_
F-68 | S6 | M0/Survey | Done | M1 regulation service: `list_regulations`, `get_regulation`, `get_regulation_sectors`, `create_regulation`, `update_regulation`, `verify_regulation`.
F-69 | S6 | M0/Survey | Done | Backend routers + schemas: `/api/v1/survey-flow/{start,answer}` (SME) and `/api/v1/m1/regulations/*` (admin CRUD + `/{id}/public` SME-safe read). Moun
F-70 | S6 | M3 Risk | Done | M3 projection on `survey_service.submit`: `_project_m3_snapshots` writes `module_number = 3` answers into `m3_compliance_history` / `m3_behavioural_si
F-71 | S6 | M0/Survey | Done | Unified `/surveys` page (server) + `SurveyWizard` client + `flow-question-to-ui.ts` adapter (single/multi/likert/date/numeric/short_text/ordered_steps
F-72 | S6 | M0/Survey | Done | i18n parity: new `surveys.flowTitle / flowSubtitle / questionOfTotal / crossModuleHint` keys added to `en/si/ta`. ¦ 🟢 ¦ session 6 ¦ All three locales
F-73 | S6 | M2 Knowledge | Done | Follow-up migration `202605100002_relax_survey_question_columns.py` — drops `NOT NULL` from `survey_questions.domain_code` and `knowledge_type` so M0
F-74 | S7 | M0/Survey | In Progress | Phase A landed (session 7).
F-75 | S6 | M3 Risk | Not Started | Backend tests: extend `test_m2_scoring.py` (M3 answers don't get scored); new `test_survey_flow.py` (start → answer → branch → null, incl. resume); ne
F-76 | S6 | M0/Survey | Not Started | Playwright spec: `surveys_unified_flow.spec.ts` walking the VAT-no branch into `VAT_FACT_002` and verifying the module-accent swap ¦ 🔲 ¦ session 6 pla
F-77 | S7 | M0/Survey | Not Started | Phase B (deferred).
F-78 | S7 | M0/Survey | Done | New `Tabs` primitive (`components/ui/tabs.tsx`) on `@radix-ui/react-tabs` (already in deps). Reused by the regulation form's EN/SI/TA panels; availabl
F-79 | S7 | M2 Knowledge | Done | Per-module accent extended into admin shells: `module-m2` wraps `/admin/m2/questions` and `/admin/m2/scores`; `module-m3` wraps `/admin/m3/risk-signal
F-80 | S7 | M0/Survey | Done | i18n keys for the regulations admin surface (en/si/ta parity at 185 keys each): `nav.adminRegulations`, `regulations.{listTitle, listSubtitle, newTitl
F-81 | S7 | M1 Awareness | Done | Constants extracted to single source of truth: `lib/constants/domains.ts` (DOMAINS) and `lib/constants/sectors.ts` (SECTORS + DOCUMENT_TYPES) — used b
F-82 | S8 | Platform/Foundation | Done | Hotfix: parallel-pages route collision
F-83 | S8 | Platform/Foundation | Done | App-shell redesign.
F-84 | S8 | Platform/Foundation | Done | New shell primitives + glue: `components/ui/avatar.tsx` (initials fallback), `components/ui/breadcrumb.tsx`, `components/ui/tooltip.tsx` (radix-toolti
F-85 | S8 | Platform/Foundation | Done | Dashboard upgrade.
F-86 | S8 | Platform/Foundation | Done | List-page polish.
F-87 | S8 | Platform/Foundation | Done | **i18n: `dashboard.*` (welcome + stats + tasks + activity) + `topbar.*` (refresh / avatarLabel / signOut / sidebarToggle) added across en/si/ta. Parit
F-88 | S8 | Platform/Foundation | Done | Form-page polish.
F-89 | S9 | M0/Survey | Done | Survey-wizard dotted-field-name bug fix.
F-90 | S9 | M3 Risk | Done | Module 4 data-collection research scaffolding.
F-91 | S10 | M0/Survey | Done | Sticky desktop sidebar + mobile drawer (hamburger trigger).
F-92 | S10 | M0/Survey | Done | `/admin/users` redesign
F-93 | S10 | M0/Survey | Done | Searchable multi-select Combobox primitive
F-94 | S10 | M0/Survey | Done | Admin-create-user endpoint + dialog.
F-95 | S10 | M0/Survey | Done | Two runtime bug fixes.
F-96 | S10 | M0/Survey | Done | Backend full CRUD for users.
F-97 | S10 | M0/Survey | Done | Backend full CRUD for regulations + soft-archive migration.
F-98 | S10 | M0/Survey | Done | Frontend full CRUD UI
F-99 | S10 | M0/Survey | Done | `<SurveyForm>` dotted-id leak (per-instrument awareness page).
F-100 | S11 | M0/Survey | Done | Backend admin survey-questions CRUD.
F-101 | S11 | M0/Survey | Done | `<QuestionForm>` + `/admin/questions/{list,new,[code]/edit}` pages.
F-102 | S11 | M0/Survey | Done | `<BranchingRulesEditor>` (Visual + JSON tabs).
F-103 | S11 | M0/Survey | Done | Regulation-anchored authoring wizard + LinkedQuestionsPanel.
F-104 | S11 | M0/Survey | Done | i18n: `questions.*`, `regulations.linkedQuestionsPanel.*`, `regulations.authoring.*`, `nav.adminQuestions`, `common.previous`.
F-105 | S11 | M2 Knowledge | Done | Sidebar entry `nav.adminQuestions` + deprecation note on the legacy M2 list.
F-106 | S12 | M0/Survey | Done | Branching validators (forward-ref / cycle / archived-target).
F-107 | S12 | M0/Survey | Done | Regulation-scoped flow.
F-108 | S12 | M0/Survey | Done | M:N junction `survey_question_regulations`.
F-109 | S12 | M0/Survey | Done | Backend i18n fallback.
F-110 | S12 | M0/Survey | Done | DB-driven per-instrument question fetch.
F-111 | S12 | M0/Survey | Done | Translation queue admin.
F-112 | S12 | M0/Survey | Done | Dashboard pending-regulations endpoint.
F-113 | S12 | M0/Survey | Done | Visual flow canvas.
F-114 | S12 | M0/Survey | Done | DB-driven per-module SME surveys.
F-115 | S12 | M0/Survey | Done | Two-tab surveys hub + regulation-scoped flow page.
F-116 | S12 | M0/Survey | Done | Dashboard widget — Regulations awaiting your assessment.
F-117 | S12 | M0/Survey | Done | Translations admin page + sidebar nav.
F-118 | S12 | M0/Survey | Done | Frontend types + API extensions.
F-119 | S13 | Platform/Foundation | Done | `<AnimatedLoadingSkeleton>` (`components/ui/`) — theme-adapted shadcn-pattern component.
F-120 | S13 | Platform/Foundation | Done | Streaming `loading.tsx` segments + skeleton wiring across the app.
F-121 | S13 | Platform/Foundation | Done | New SETUP doc `12_UI_Screens_and_Loading.md`.
F-122 | S13 | Platform/Foundation | Done | App-themed `<Pagination>` (`components/ui/`), wired into all eight admin tables.
F-123 | S13 | Platform/Foundation | Done | QA bug-fix batch.
F-124 | S14 | Platform/Foundation | Done | Audit-write consolidation + coverage closure.
F-125 | S14 | Platform/Foundation | Done | `AuthorshipMixin` — `created_by` / `updated_by` everywhere it matters.
F-126 | S14 | Platform/Foundation | Done | Admin Activity Log API.
F-127 | S14 | Platform/Foundation | Done | Admin Activity Log UI.
F-128 | S14 | Platform/Foundation | Done | Authorship footer on the admin edit pages.
F-129 | S15 | M3 Risk | Done | `survey_responses.linked_regulation_id` populated end-to-end.
F-130 | S15 | M3 Risk | Done | `meta.from_question_code` / `meta.from_rule` flow breadcrumb + `start_flow` fallback.
F-131 | S15 | M3 Risk | Done | Worked end-to-end scenario `VAT_SSCL_MERGE_2026` seeded.
F-132 | S15 | M3 Risk | Done | OQ32-class follow-up resolved — data-driven M3 question→risk-column mapping.
F-133 | S15 | M3 Risk | Done | Docs reconciliation + sidebar `/surveys` consolidation.
F-134 | S16 | M0/Survey | Done | `survey_limits` DB singleton + service.
F-135 | S16 | M0/Survey | Done | Admin survey-limits API + wiring.
F-136 | S16 | M0/Survey | Done | Admin settings frontend page.
F-137 | S16 | M0/Survey | Done | Sidebar nav + i18n for admin settings.
F-138 | S17 | M0/Survey | Done | `get_limits` catches `ProgrammingError` + rolls back session.
F-139 | S18 | Platform/Foundation | Done | Documentation sync across all affected MD files.
F-140 | S19 | M2 Knowledge | Done | M2/M3/M4 feature detail documentation sweep (SETUP + research).
F-141 | S19 | M2 Knowledge | Done | Tracker update — Session 19.
F-142 | S20 | M2 Knowledge | Done | Domain-based documentation restructuring (Session 20).
F-143 | S21 | Platform/Foundation | Done | M1 doc cleanup: section-header conformance + folder-path consistency sweep (Session 21).
F-144 | S22 | Platform/Foundation | Done | Backend seed refactor — demo dashboards populated on `make seed`.
F-145 | S23 | M1 Awareness | Done | M1 Phase 2 Step 2a — Scrapy gazette spider MVP (Session 23).
F-146 | S24 | Platform/Foundation | Done | `planned-for-devlopment/` folder convention + Step 2a setup doc + Vercel URLs noted (Session 24).
F-147 | S25 | Platform/Foundation | Done | Step 2a parse-bug fix + Step 2b planning docs (Session 25).
F-148 | S26 | M1 Awareness | Done | M1 Phase 2 Step 2b — Celery + Stage-B PDF extraction (Session 26).
F-149 | S28 | M1 Awareness | Done | M1 Phase 2 Step 2c — canonical extraction chain at `enigmatrix-ml/m1/extraction/` (Session 28).
F-150 | S29 | M0/Survey | Done | Auth pages split-panel UI (Session 29).
F-151 | S29 | M0/Survey | Done | M1 docs portal data consolidation (Session 29).
F-152 | S29 | M0/Survey | Done | Admin survey config: unified module option + multi-sector checkboxes — frontend only (Session 29).
F-153 | S30 | M1 Awareness | Done | M1 Phase 2 Step 2d — language detection + Wijesekara conversion + per-page OCR fallback (Session 30).
F-154 | S31 | M1 Awareness | Done | M1 Phase 2 Step 2e — Preprocessing chain at `enigmatrix-ml/m1/preprocessing/` (Session 31).
F-155 | S32 | M1 Awareness | Done | M1 Phase 2 Step 2f — Celery wiring + DB persistence for the Step-2e preprocessing chain (Session 32).
F-156 | S33 | Platform/Foundation | Done | M1 Phase 2 doc-only catch-up (Session 33).
F-157 | S34 | Platform/Foundation | Done | M1 Phase 2 cleanup (Session 34).
F-158 | S35 | Platform/Foundation | Done | Local-dev documentation lap (Session 35).
F-159 | S36 | Platform/Foundation | Done | Research-log portal (Session 36).
F-160 | S37 | M1 Awareness | Done | M1 Pipeline observability portal (Session 37).
F-161 | S38 | M1 Awareness | Done | Year + month-range scoped gazette extraction trigger (Session 38).
F-162 | S38 | M1 Awareness | Done | Celery eager-mode + pytest-asyncio session-loop fix for integration tests (Session 38).
F-163 | S39 | M1 Awareness | Done | Token-key sweep across 7 M1 admin pages (Session 39).
F-164 | S39 | M1 Awareness | Done | Gazette Extraction page UX enrichments — trigger history + summary card + per-row chips (Session 39).
F-165 | S40 | M1 Awareness | Done | M1 Pipeline in-page sub-nav: Gazette Extraction entry (Session 40).
F-166 | S40 | M1 Awareness | Done | Postgres connection-limit hotfix for the extract→preprocess fan-out (Session 40).
F-167 | S41 | M1 Awareness | Done | Pipeline-flow tiles surface a cumulative "reached" count (Session 41).
F-168 | S41 | M1 Awareness | Done | Aiven cloud-Postgres pool sizing fix (Session 41).
F-169 | S42 | M1 Awareness | Done | Date-range picker for Gazette Extraction (FE + BE, Session 42).
F-170 | S43 | Platform/Foundation | Done | Spider runtime fix — close spider when scope exhausted (Session 43).
F-171 | S44 | Platform/Foundation | Done | Theme polish (Session 44).
F-172 | S45 | M1 Awareness | Done | M1 pipeline page responsiveness v2 (Session 45).
F-173 | S46 | M1 Awareness | Done | Extraction running UX upgrade (Session 46).
F-174 | S47 | Platform/Foundation | Done | Frontend perf overhaul (Session 47).
F-175 | S49 | Platform/Foundation | Done | Live count polling for `summaryForResume` (Session 49).
F-176 | S49 | Platform/Foundation | Done | `SpiderResultCard` polished display (Session 49).
F-177 | S50 | Platform/Foundation | Done | Completeness check + re-fetch + spider EN→SI→TA fallback (Session 50).
F-178 | S51 | Platform/Foundation | Done | Completeness verify endpoint hardening (Session 51).
F-179 | S52 | Platform/Foundation | Done | AnimatedList component suite (Session 52).
F-180 | S52 | Platform/Foundation | Done | AnimatedItem applied to 6 list/card pages + sticky table headers across 13 table files (Session 52).
F-181 | S52 | Platform/Foundation | Done | FuzzyText component (Session 52).
F-182 | S52 | Platform/Foundation | Done | FuzzyText applied to 404, ComingSoon, Platform Map, Research Log (Session 52).
F-183 | S52 | Platform/Foundation | Done | Theme toggle: dropdown → single-click toggle button + View Transitions API circular reveal (Session 52).
F-184 | S53 | M1 Awareness | Done | M1 pipeline admin UX/UI audit — 14-finding report (Session 53).
F-185 | S54 | M1 Awareness | Done | Sticky M1 extraction inner sidebar (Session 54).
F-186 | S54 | M1 Awareness | Done | Resume/restart extraction for partial-state runs (Session 54).
F-187 | S54 | M1 Awareness | Done | Full extraction history table — replaces 5-item pill strip (Session 54).
F-188 | S54 | M1 Awareness | Done | Auto-scroll to progress panel on history row select (Session 54).
F-189 | S54 | M1 Awareness | Done | `m1_extraction_runs` DB model + Alembic migration (Session 54).
F-190 | S54 | M1 Awareness | Done | Backend: persist run on trigger + status sync on poll/cancel + `GET /runs` endpoint (Session 54).
F-191 | S54 | M1 Awareness | Done | Frontend: run history from `GET /runs` + localStorage write-through cache (Session 54).
F-192 | S54 | M1 Awareness | Done | SQLAlchemy QueuePool fix — `pool_size=3`, `max_overflow=5` (Session 54).
F-193 | S55 | Platform/Foundation | Done | Railway production deployment of `enigmatrix-backend` (Session 55).
F-194 | S55 | M1 Awareness | Done | Cancel + rollback admin endpoint — `POST /api/v1/admin/m1/extraction/cancel/{task_id}` (Session 55).
F-195 | S55 | M1 Awareness | Done | Cancel button + ConfirmDialog + inline result panel on extraction status card (Session 55).
F-196 | S55 | M1 Awareness | Done | Per-PDF metadata columns + extract-time population (migration `202605280001` + `pdf_metadata.py` helper) (Session 55).
F-197 | S55 | Platform/Foundation | Done | PDF Records browse-all admin page — `/admin/m1/pdf-records` + `GET /pdf-records` endpoint (Session 55).
F-198 | S55 | Platform/Foundation | Done | Cross-repo Stage 4 code-quality audit + three HIGH inline fixes (Session 55).
F-199 | S56 | M1 Awareness | Done | M1 raw PDF bulk extraction + classification — 800 PDFs across 11 batches (Session 56).
F-200 | S57 | M1 Awareness | Done | Slice 3 — backend-local XLSX parser wrapper + ML parser handle close (Session 57).
F-201 | S57 | M1 Awareness | Done | Slice 3 — reproducible 5-row M1 master xlsx test fixture (Session 57).
F-202 | S57 | M1 Awareness | Done | Slice 3 — parser unit test suite (Session 57).
F-203 | S57 | M1 Awareness | In Progress | Slice 3 — upload integration test suite (Session 57).
F-204 | S57 | M1 Awareness | Done | Slice 3 — `/admin/m1/datasets/new` create page + form component (Session 57).
F-205 | S57 | M1 Awareness | In Progress | Slice 3 — Playwright E2E spec for create/upload/promote/idempotency (Session 57).
F-206 | S58 | M1 Awareness | Done | Datasets restructure — i18n migration m1Datasets.* → datasets.m1.* + new datasets.hub.* namespace (Session 58).
F-207 | S58 | M1 Awareness | Done | Datasets restructure — moved M1 pages under /admin/datasets/m1/* + new hub at /admin/datasets (Session 58).
F-235 | S68 | M1 Awareness | Unknown | Phase 4c — lag materialized views + drift helper (Session 68).
F-236 | S68 | M1 Awareness | In Progress | Phase 4c — nightly analytics task + Beat (Session 68).
F-237 | S69 | M1 Awareness | Done | Phase 5b — findings_common helpers + preregistration (Session 69).
F-238 | S69 | M1 Awareness | In Progress | Phase 5b — 4 findings notebooks F1–F6 (Session 69).
F-239 | S70 | M1 Awareness | Done | Phase 5c — m1_retraining_runs + canary promotion decision (Session 70).
F-240 | S70 | M1 Awareness | In Progress | Phase 5c — retrain.py + retraining task + triggers (Session 70).
F-241 | S71 | M1 Awareness | Done | P0 hygiene — F1-gate reconcile + MASTER_CONTEXT refresh + deliverables regen (Session 71).
F-242 | S72 | M1 Awareness | Done | Extraction accuracy-report export + measurement UI audit (Session 72).

## Roadmap vs Actual
Phase | Step | Planned | Definition of Done | Status | Evidence | Notes | Score
Phase 1 — Foundation | — | Admin regulation CRUD+verify, audit, unified survey, seed | Shipped | Done | F-65..F-97 (S6–22) | Baseline. | 1
Phase 2 — Ingest+Extract | 2a Scrapy spider | gazette/weekly/acts/bills → ingested | N ingested rows | Done | F-144/145 (S23) |  | 1
Phase 2 — Ingest+Extract | 2b Celery extract | extract_gazette → extracted | row→extracted | Done | F-148 (S26) |  | 1
Phase 2 — Ingest+Extract | 2c Extraction chain | ml/m1/extraction multi-engine | ≥95% classify | Done | F-149 (S28) |  | 1
Phase 2 — Ingest+Extract | 2d Lang+Wijesekara | fastText + legacy Sinhala | ≥95% lang acc | Done | F-153 (S30) |  | 1
Phase 2 — Ingest+Extract | 2e/2f Preprocess+persist | cleaning+metadata+chunk → preprocessed | metadata populated | Done | F-154/155 (S31/32) |  | 1
Phase 2 — Ingest+Extract | Upgrade (slices 1–9) | datasets+profiles+measurement engine | measure extraction quality | Done | F-200..F-215 (S57–60) | Beyond original. | 1
Phase 3 — Annotation+Classify | 3a LS + calibration | LS config + calibration set | κ≥0.80 | In Progress | F-216/217 (S61) | annotators pending. | 0.5
Phase 3 — Annotation+Classify | 3b Sampling | samplers + batch_01 | batch_01 200 | Done | F-218-220 (S61) |  | 1
Phase 3 — Annotation+Classify | 3c Gold ≥800 | annotate to 800 | 800 gold κ≥0.75 | Not Started | planned F-222 | needs annotators. | 0
Phase 3 — Annotation+Classify | 3d Train XLM-R+LoRA | m1/model + training | 3-seed F1≥0.92 | In Progress | F-226 (S63) | scaffold built; train pending. | 0.5
Phase 3 — Annotation+Classify | 3e Eval+baselines | eval.py + baselines.py | no slice cliff>8pp | In Progress | F-227 (S64) | scaffold built. | 0.5
Phase 3 — Annotation+Classify | 3f ONNX+wiring | export+inference+classify_gazette | INT8 1.5pp; p95≤2s | In Progress | F-228 (S65) | wired; export/deploy pending model. | 0.5
Phase 4 — Schedulers+Alerts+Lag | 4a Portal+RSS watchers | watchers → m1_propagation_events | events w/ confidence | In Progress | F-229-231 (S66) | built+matcher tested; live pending network. | 0.5
Phase 4 — Schedulers+Alerts+Lag | 4b Alert dispatch + web feed | in-app/email/SMS + /alerts page | ≤1h; idempotent | In Progress | F-232-234 (S67) | built; live pending migration/keys. | 0.5
Phase 4 — Schedulers+Alerts+Lag | 4c Nightly view refresh + drift | materialized views + KL drift | drift fires | In Progress | F-235-236 (S68) | built+drift tested; live pending data. | 0.5
Phase 5 — Findings+Survey | 5a SME survey deployment | wire /portal/m1/survey; outreach | ≥100 respondents | In Progress | M0 survey F-33-36 | instrument live; fieldwork pending. | 0.5
Phase 5 — Findings+Survey | 5b F1–F6 findings notebooks | 4 findings_*.ipynb + preregistration | median+CI+test each | In Progress | F-237-238 (S69) | built+demo runs; real data pending. | 0.5
Phase 5 — Findings+Survey | 5c Retraining + rollback | retrain.py + canary + m1_retraining_runs | dry-run + rollback | In Progress | F-239-240 (S70) | built + dry-run tested; real run pending model+GPU. | 0.5

## Manual Test Plan
Manual Test Plan — flows, expected outcomes & next steps
One test per segment (done + pending + not-started). "Runnable" = can you run it today.
Runnable now | 7
Pending (prereq) | 9
Not built yet | 1
Test ID | Phase / Segment | Feature | Why (objective) | Preconditions | Test steps (flow) | Expected outcome | Runnable | Status | What next
T-01 | Phase 1 · CRUD | Admin regulation CRUD | Confirm regs enterable + verifiable (ground truth). | Backend+frontend up; admin seeded. | 1. Login admin 2. /admin/regulations → New → save 3. detail → Verify 4. check Activity Log | Reg in list; verified; audit_log row. | Now | Pass (verify) | —
T-02 | Phase 1 · Survey | Awareness survey EN/SI/TA | RQ1 instrument works trilingually. | Seeded; demo SME. | 1. Login SME 2. /surveys/awareness switch EN→SI→TA 3. answer 12 + submit 4. admin responses view | Response saved + visible; all langs render. | Now | Pass (verify) | —
T-03 | Phase 2 · Spider | Scrapy gazette spider | Automated gazette discovery. | Redis+backend; storage writable. | 1. scrapy crawl gazette_spider (or admin trigger) 2. watch run | N PDFs + N ingested rows. | Now | Pass (verify) | —
T-04 | Phase 2 · Extract→Preprocess | extract+preprocess pipeline | PDFs → clean chunked text + metadata. | Worker running; an ingested row. | 1. start celery worker 2. extract_gazette → preprocess chains 3. query row | ingested→extracted→preprocessed; metadata populated. | Now | Pass (verify) | —
T-05 | Phase 2 · Extraction chain | ml/m1/extraction tests | Multi-engine routing correct. | cd enigmatrix-ml. | 1. uv run pytest tests/m1/extraction -v | extraction tests pass; CER audit skips (no gold). | Now | Partial (gold pending) | populate 50-PDF audit.
T-07 | Phase 2 · Upgrade | Dataset + measurement | Extraction quality measured vs golden. | Backend up; golden xlsx. | 1. /admin/datasets/m1 → create → upload golden 2. run extraction+measurement 3. comparison view | Measurement run + per-field scores. | Now | Pass (verify) | —
T-09 | Phase 3 · 3b Sampling | sample_for_labeling | Diverse first batch. | cd enigmatrix-ml. | 1. python scripts/sample_for_labeling.py --demo --dry-run 2. --demo | batch_01.csv 200 rows, 3 langs. | Now | Pass (demo) | make labeling-batch on prod DB.
T-10 | Phase 3 · 3c Gold | Annotate ≥800 | Training data (RQ1 gate). | 3a passed. | 1. make labeling-batch → Label Studio 2. AL batches + dual-annotate 3. export gold_standard.csv | ≥800 labels ≥50/cat κ≥0.75. | Not built | Not built | recruit annotators.
T-11 | Phase 3 · 3d Model | m1/model tests + train | Classifier code correct + trainable. | uv sync --extra training; gold split. | 1. uv run pytest tests/m1/model 2. mini-smoke train 3. train_xlmr 3-seed | label/data tests pass now; full run F1≥0.92. | Pending | Partial (label/data tests pass) | after 3c + GPU.
T-12 | Phase 3 · 3e Eval | eval + baselines | Prove F1≥0.92 + baselines. | trained model + test.parquet. | 1. m1.model.eval 2. m1.model.baselines | metrics.json F1≥0.92, no cliff>8pp. | Pending | Pending | run after 3d.
T-13 | Phase 3 · 3f Inference | classify_gazette e2e | Auto-classify preprocessed gazette. | migration + ONNX model + M1_MODEL_ONNX_DIR. | 1. alembic upgrade head 2. export_onnx --int8 3. worker classify_gazette 4. integration test | preprocessed→classified; low-conf→review. | Pending | Pending | run after 3d/3e.
T-14 | Phase 4 · 4a Watchers | portal/rss watchers | Timestamp downstream mentions → lag. | uv sync (feedparser); alembic upgrade head. | 1. pytest test_m1_propagation_matching 2. run_rss_watcher.apply() 3. query m1_propagation_events | matcher tests pass now; live run writes events w/ match_method+confidence. | Pending | Partial (matcher tested) | confirm source URLs + apply migration.
T-15 | Phase 4 · 4b Alerts+feed | alert dispatch + /alerts | Sector-matched alerts + website feed. | alembic upgrade head. | 1. dispatch_regulation_alerts.apply([reg]) 2. GET /m1/alerts/public 3. visit /alerts | in-app alerts created (email 'skipped' w/o key); public feed renders. | Pending | Partial (content tested) | set SendGrid/Twilio; wire middleware/nav.
T-16 | Phase 4 · 4c Analytics | lag views + drift | Nightly refresh + drift check. | alembic upgrade head (202606300004). | 1. pytest test_m1_drift 2. refresh_lag_analytics.apply() 3. SELECT * FROM v_m1_channel_effectiveness | drift tests pass now; views refresh; drift_kl returned. | Pending | Partial (drift tested) | run after 4a data + 3f classified.
T-17 | Phase 5 · 5a Survey | Survey deployment | Awareness lag data (RQ3). | /portal/m1/survey wired. | 1. wire 9-reg SQL 2. NEDA/Chamber outreach + ethics 3. track by sector | ≥100 respondents, ≥10/sector. | Pending | Pending | deployment + outreach.
T-18 | Phase 5 · 5b Findings | F1–F6 notebooks | Empirical RQ1/RQ3/RQ4 answer. | uv sync --extra research. | 1. pytest tests/research/test_findings_common.py 2. Run-All each notebook (demo) 3. set DATABASE_URL for real data | helpers tests pass; notebooks compute F1–F6 on demo (F1≈6.8d, F6 DiD≈-20d); real numbers pending data. | Pending | Partial (demo runs) | run on real data after 4a/5a/3d.
T-19 | Phase 5 · 5c Retraining | retrain + rollback | Sustain model quality; drift(4c) triggers. | alembic upgrade head (202606300005). | 1. pytest tests/m1/model/test_promotion.py 2. retrain.py --dry-run 3. run_retraining.apply(dry_run=True) | promotion tests pass; --dry-run returns a decision; real retrain pending model+GPU. | Pending | Partial (dry-run runs) | run real retrain after 3d/3e.

## Status Rollup
Status Rollup
Status | Count | % of features
Done | 205 | 95.35%
In Progress | 6 | 2.791%
Not Started | 3 | 1.395%
Blocked | 0 | 0%
Dropped | 0 | 0%
Unknown | 1 | 0.4651%
TOTAL | 215 | 100%

## Gaps & Next
Gaps & Next Actions
Priority | Item | Status | Unlocks | Next action
P0 | Fix /admin/m1/pipeline/recent 503 (F-184) + reconcile F1 gate 0.80↔0.92 | In Progress | Demo integrity; correct thesis bar | fix RSC 503; grep-replace 0.80→0.92.
P1 | 3c — Annotate to ≥800 gold labels | Not Started | RQ1 training data | recruit annotators; make labeling-batch; calibrate; AL to 800.
P1 | 3d/3e/3f — train + eval + deploy classifier | In Progress | RQ1 macro-F1≥0.92 + operational | after gold: uv sync --extra training; train on GPU; export ONNX; alembic upgrade head.
P1 | Apply Phase-3/4 migrations (202606300001–004) | In Progress | Classifier + propagation + alerts + lag views live | cd enigmatrix-backend && uv run alembic upgrade head.
P2 | 4a/4b/4c — run watchers + alerts + analytics live | In Progress | Lag dataset + alert system + monitoring | uv sync; confirm source URLs; run watchers; set SendGrid/Twilio; refresh_lag_analytics.
P2 | Frontend /alerts wiring (middleware + nav + client) | In Progress | Public + SME alerts section live | add /alerts to middleware public routes; nav link; align lib/api/client.ts.
P3 | 5a — SME survey deployment (≥100) | In Progress | RQ3 awareness-lag data | wire /portal/m1/survey; NEDA/Chamber; ethics.
P3 | 5b — run F1–F6 on real data | In Progress | Empirical thesis result | uv sync --extra research; preregister; Run-All notebooks with DATABASE_URL.
P3 | 5c — Retraining + auto-rollback | Not Started | Sustainable model ops | retrain.py + canary + m1_retraining_runs.
Data | SI/TA raw_text (cid:) re-extraction | Not Started | RQ2 (SI/TA F1) integrity | re-extract SI/TA via OCR+Wijesekara before gold text.